## ATC
Assigned Task Chart
ISYS321, Instructor: Dr. Amy Buse |  |  |  |  | Team Number | 6
Team Membr Names: |  |  | Kyle Gottfried, Kyle Thompson, Cale Kuchnicki
| Signifies complete/started | Signifies Late | Signifies Not Complete
Task # | Task | Component Of | Assigned to | Work Started | Expected Completion Date | Actual Completion Date
29 | Create MySQL Database | Checking Phase | Kyle Gottfried |  | 2014-02-24 | 2014-02-19
31 | Create Respository | Checking Phase | Kyle Gottfried |  | 2014-02-24
32 | Create Heading Page (Frontend) | Checking Phase | Cale Kuchnicki |  | 2014-02-24 | 2014-02-24
34 | Create Login Page (frontend) | Checking Phase | Kyle Gottfried |  | 2/30/2014
33 | Create Search page (frontend) | Checking Phase | Kyle Thompson |  | 2/30/2014
30 | Create Search Results page (frontend) | Checking Phase | Kyle Thompson |  | 2/30/2014
28 | Data Dictionary | Design Phase | Kyle Gottfried |  | 2014-02-17 | 2014-02-16
27 | Data Flow Diagram | Design Phase | Kyle Thompson |  | 2014-02-17 | 2014-02-24
25 | Entity Relationship Diagram | Design Phase | Kyle Gottfried |  | 2014-02-17 | 2014-02-16
23 | Event Response Table | Design Phase | Cale Kuchnicki |  | 2014-02-17 | 2014-02-17
11 | File Structure | Design Phase | Kyle Gottfried |  | 2014-02-17 | 2014-02-13
26 | Sample Process Specification | Design Phase | Kyle Thompson |  | 2014-02-17 | 2014-02-24
22 | Site Map | Design Phase | Kyle Thompson |  | 2014-02-17 | 2014-02-17
2 | Team Meeting Notes | Design Phase | Kyle Thompson |  | 2014-02-03 | 2014-02-10
3 | Team Meeting Notes | Design Phase | Kyle Thompson |  | 2014-02-10 | 2014-02-10
4 | Team Meeting Notes | Design Phase | Kyle Thompson |  | 2014-02-17 | 2014-02-17
8 | Use Case Diagrams/Tables | Design Phase | Team |  | 2014-02-17 | 2014-02-24
21 | Web Site and Form Design | Design Phase | Kyle Thompson\Cale Kuchnicki |  | 2014-02-17 | 2014-02-04
35 | Finish Project | Final Phase | Team |  | 2014-04-21
7 | Scope Statement | Planning Phase | Kyle Thompson |  | 2014-01-15 | 2014-01-15
5 | Create Team Charter | Planning Phase | Team |  | 2014-01-16 | 2014-01-16
24 | Submit Team Assignment #4 | Planning Phase | Kyle Gottfried |  | 2014-01-16 | 2014-01-16
6 | Submit Team Charter | Planning Phase | Cale Kuchnicki |  | 2014-01-16 | 2014-01-16
10 | Team Meeting Notes | Planning Phase | Kyle Thompson |  | 2014-01-20 | 2014-01-21
9 | Task List | Planning Phase | Kyle Gottfried |  | 2014-01-21 | 2014-01-16
36 | Ask 3 questions for client to answer | Planning Phase | Kyle Gottfried |  | 2014-01-23 | 2014-01-23
37 | Ask 3 questions for client to answer | Planning Phase | Cale Kuchnicki |  | 2014-01-23 | 2014-01-23
38 | Ask 3 questions for client to answer | Planning Phase | Kyle Thompson |  | 2014-01-23 | 2014-02-05
1 | Team Meeting Notes | Planning Phase | Kyle Thompson |  | 2014-01-27 | 2014-02-03
39 | Update Scope Statement | Planning Phase | Team |  | 2014-01-27
12 | Team Meeting Notes |  | Kyle Thompson |  | 2014-02-24
13 | Team Meeting Notes |  | Kyle Thompson |  | 2014-03-03
14 | Team Meeting Notes |  | Kyle Thompson |  | 2014-03-10
15 | Team Meeting Notes |  | Kyle Thompson |  | 2014-03-17
16 | Team Meeting Notes |  | Kyle Thompson |  | 2014-03-24
17 | Team Meeting Notes |  | Kyle Thompson |  | 2014-03-31
18 | Team Meeting Notes |  | Kyle Thompson |  | 2014-04-07
19 | Team Meeting Notes |  | Kyle Thompson |  | 2014-04-14
20 | Team Meeting Notes |  | Kyle Thompson |  | 2014-04-21
40 | Create Event Creation page (frontend) | Checking Phase | Cale Kuchnicki |  | 2/30/2014
41 | Create Registration page (frontend) | Checking Phase | Cale Kuchnicki |  | 2/30/2014
42 | Create Account Tools page (frontend) | Checking Phase | Kyle Gottfried |  | 2/30/2014
43
44
45
46
47
48
49
50
51
52
53
54

## Directions
Purpose: To hold team members accountable to their tasks with expected due dates.
Usage: When doing any kind of project, planning and effective communications are a must. The Assigned Task chart (ATC) is used to facilitate the planning component of a project. A project that is not well planned takes twice as long as a project that is well planned. The minimum planning required in this class is a three-step process.
Step 1:
Each team member reads the specifications of the project and fills out a KND chart by themselves without talking to their team member(s). Each team member will start by filling out the first column by answering the question – what do I Know about this project. Be very specific with things that are already known, facts, due dates, anything. Then move to the middle column and ask the question, what do we Need to know to finish this project. And then finally, the last column is completed with a list of tasks that need to be completed for a successful project is created. This is all done individually to make sure that each team member understands the full scope of the project and is prepared for the project.
Step 2:
The team gets together, reviews the individual KND charts to make sure all aspects of the project have been thought about, and all steps to a successful project have been identified. The team then takes all the tasks in the ‘Do’ column of the KNDs, and turns them into tasks for the ATC. Each task is assigned to a team member with an expected completion date for that task. Remember that all tasks cannot wait until the actual due date for the project. As the team meets to complete the tasks, meeting notes are kept using the meeting notes form.
Step 3:
As each task is completed the team will fill-in the ‘Actual Completion Date’ column of the ATC. When all tasks are completed, the team should be asking what tasks were performed that were not on the original task list, and how well did the team do setting due dates for each task.
.
This form must be typed and there is only one form per team.
KND Charts are not required, but encouraged.

## Tasks for ATC
Attendence
Group Meeting Time | Instructor Meeting Time | Kyle Gottfried |  | Kyle Thompson |  | Cale Kuchnicki
4:30PM | 1:30PM | Group | Instructor | Group | Instructor | Group | Instructor
2014-01-21 | 2014-01-23
2014-01-27 | 2014-01-30
2014-02-03 | 2014-02-06
2014-02-05
2014-02-10 | 2014-02-13
2014-02-12
2014-02-17 | 2014-02-20
2014-02-24 | 2014-02-27
2014-03-03 | 2014-03-06
2014-03-10 | 2014-03-13
2014-03-17 | 2014-03-20
2014-03-24 | 2014-03-27
2014-03-31 | 2014-04-03
2014-04-07 | 2014-04-10
2014-04-14 | 2014-04-17
2014-04-21 | 2014-04-24
Person assigned to review the team's work before submitting assignment: |  |  |  | Kyle Thompson
Submit the Assignment: |  |  |  | Cale Kuchnicki
The ATC is how the team will keep track of who is doing what with regards to the team assignments.
It is a document that will start with this assignment and grow for the entire semester.
It should include tasks such as
- team meetings (date, time, location/online tool) team meetings for the entire semester should be scheduled as
soon as possible and stated in the team charter
- assignment tasks (who will do what part of the assignment)
- who/when will review the team’s work before submitting the assignment
- who will submit the assignment
Holding team members accountable is done by using the ATC. If you have a team member who is not pulling their weight the ATC and the team evaluations are the two ways to most effectively communicate that to the instructor.